## Sheet1
Task	description	estimate	progress	notes
overall chart ui	fancy up	2-3 days
monthly chart			done	there cloud be an option to select
yearly chart			done	which year/month
all chart			done	to preview
coin data collection		20 min	80.00%	need to update the data nearing final sprint

nav bar		in progress

home page		5-6 days
individual coin page		1-2 days
coin selection page		1-2 days
wallet page		1-2 days
user login page		1-2 days
users		1-2 days
database		3-4 days	10.00%	just an initial setup and connection with django